## Gantt Timeline
[6 empty] | september 2026 г. | октябрь 2026 г. | [30 empty] | ноябрь 2026 г.
Workstream | Task Name | Assignees | Start Date | End Date | Duration | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05
Planning | Conduct dataset search and selection | Project Team | 2026-10-07 | 2026-10-07 | 1
Planning | Define project objectives and planning | Project Team | 2026-10-08 | 2026-10-08 | 1
Data Preparation | Check and remove duplicate records | Project Team | 2026-10-09 | 2026-10-09 | 1
Data Preparation | Check missing values and data types | Project Team | 2026-10-12 | 2026-10-12 | 1
Data Preparation | Convert date columns and feature engineering | Project Team | 2026-10-13 | 2026-10-13 | 1
Analysis | Analyze sales and profit by category | Project Team | 2026-10-14 | 2026-10-14 | 1
Analysis | Analyze sales by region and segments | Project Team | 2026-10-15 | 2026-10-15 | 1
Analysis | Identify top products and discounts | Project Team | 2026-10-16 | 2026-10-16 | 1
Analysis | Perform monthly sales analysis pivot | Project Team | 2026-10-19 | 2026-10-19 | 1
Analysis | Identify key findings and trends | Project Team | 2026-10-20 | 2026-10-20 | 1
Analysis | Analyze regional and customer differences | Project Team | 2026-10-21 | 2026-10-21 | 1
Reporting | Write comprehensive project report | Project Team | 2026-10-22 | 2026-10-22 | 1
Reporting | Conduct final data analysis review | Project Team | 2026-10-23 | 2026-10-23 | 1
Reporting | Prepare data visualizations for presentation | Project Team | 2026-10-26 | 2026-10-26 | 1
Reporting | Prepare final presentation materials | Project Team | 2026-10-27 | 2026-10-27 | 1
Reporting | Conduct final project review | Project Team | 2026-10-28 | 2026-10-28 | 1
Reporting | Deliver final project presentation | Project Team | 2026-10-29 | 2026-10-29 | 1